## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project and problem statement documentation | MUST HAVE | NO | Siri Manvitha | 3- Completed
S1 | S1 | US-002 | Create system workflow and architecture diagram | MUST HAVE | US-001 | Siri Manvitha | 3- Completed
S1 | S1 | US-003 | Collect sample support tickets and knowledge base articles | MUST HAVE | NO | Siri Manvitha | 3- Completed
S2 | S2 | US-004 | Data preprocessing and text cleaning for tickets and articles | MUST HAVE | US-003 | Siri Manvitha | 3- Completed
S2 | S2 | US-005 | Use LLM to analyze article content and extract keywords | MUST HAVE | US-004 | Siri Manvitha | 3- Completed
S2 | S2 | US-006 | Group articles into categories based on semantic meaning | MUST HAVE | US-005 | Siri Manvitha | 3- Completed
S3 | S3 | US-007 | Convert ticket text into embeddings for comparison | MUST HAVE | US-006 | Siri Manvitha | 3- Completed
S3 | S3 | US-008 | Implement similarity comparison between ticket and articles | MUST HAVE | US-007 | Siri Manvitha | 3- Completed
S3 | S3 | US-009 | Display top matched articles for each ticket | MUST HAVE | US-008 | Siri Manvitha | 3- Completed
S4 | S4 | US-010 | Track which recommended article is used by agent | SHOULD HAVE | US-009 | Siri Manvitha | 3- Completed
S4 | S4 | US-011 | Store usage history for analytics | SHOULD HAVE | US-010 | Siri Manvitha | 3- Completed
S4 | S4 | US-012 | Identify repeated unmatched issues as knowledge gaps | MUST HAVE | US-011 | Siri Manvitha | 3- Completed
S5 | S5 | US-013 | Perform system testing with sample tickets | MUST HAVE | US-009 | Siri Manvitha | 3- Completed
S5 | S5 | US-014 | Deploy the system and verify integrations | MUST HAVE | US-013 | Siri Manvitha | 3- Completed
S5 | S5 | US-015 | Prepare project documentation and demo | MUST HAVE | All Tasks | Siri Manvitha | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7